## Sheet1
| Week 1 | Week 2 | Week 3 | Week 4 | Week 5 | Week 5 | Week 6 | Week 7
Start of the week | 13th June | 20th June | 27th June | 4th July | 11th July | 18th July | 1th Aug | 8th Aug
Proposal | bar: Week 1 to Week 2
Key Generation System | bar: Week 2 to Week 3
Generate the shares for the private key | bar: Week 2 to Week 3
Secret shares distribution | bar: Week 3
Signature Generation System | bar: Week 4 to Week 5
Threshold ECDSA protocol | bar: Week 4 to Week 5
State machine | bar: Week 5
Signature Generator | bar: Week 5
User Interface | bar: Week 6
Demo + user manual | bar: Week 7